## Overview
Evatec Factor - Release 10.2 - Mini Software Test Plan
Wrap-up: Actuals and analysis/comments
Rqmt/CR/Bug ID | Work Item Type |  | Timekeeping | Writing Estimate | Testing Estimate | Comments |  | Azure Writing Actuals | Azure Testing Actuals | Timekeeping Actuals | Comments
|  | Prepare Software Test Plan | Sys-Testing\plan |  | 7 |  |  |  |  | Get from TK
New Functionality
[CR ID] | CR | CR description |  | 11.5 | 35 | See 'Change Requests' tab for more details. |  | Get From Azure | Get From Azure
| Bugs | Bug description |  |  | 0.5 | See 'Bugs' tab for more details.
| n/a | Ad hoc testing | Sys-Testing\QA Test |  | 3 | See 'Change Requests' tab for more details. |  | Get From Azure | Get From Azure
|  | Total New - Writing | Sys-Testing\write | 11.5 |  | See 'Change Requests' tab for more details. |  | 0 |  | Get from TK | Comment if Azure & TK significantly different
|  | Total New - Testing | Sys-Testing\QA Test |  | 38.5 | See 'Change Requests' tab for more details. |  |  | 0 | Get from TK | Comment if Azure & TK significantly different
Regression
|  | Total Regression | Sys-Testing\regression | 0 | 4 | Allocating ad hoc verification time for exploratory testing and validation of impacted workflows not explicitly covered by formal test cases. |  | Get from Azure | Get from Azure | Get from TK
General / Other
|  | Consult time with Dev | Sys-Testing \consult |  | 3 | Because of new feature, allowing time to consult with Nicola |  |  |  | Get from TK
|  | Environment Setup, installing builds | Sys-Testing \setup |  | 1 |  |  |  |  | Get from TK
|  | Bug verification | Sys-Testing\verify |  | 10 | See 'Bugs' tab for more details. |  |  |  | Get from TK
|  | Test case and spec reviews | Sys-Testing\review |  | 4 |  |  |  |  | Get from TK
|  | Unplanned changes / contingency | Sys-Testing\misc |  | 1 |  |  |  |  | Get from TK
|  | Total General |  |  | 19 |  |  |  |  | 0
|  |  | Grand Total (estimate) |  | 80 |  | Grand Total (actual) | 0 | 0 | 0
|  | Budget: | Hours:
|  | Budget (check TK or ask PM) | 80
|  | Estimated Effort | 80
|  | Difference (hours) | 0
|  | % Difference to Budget | 0%
|  | Actual Effort (hours) | 0
|  | Actual Effort (% Diff to Budget) | -100% |  |  | Assumptions, Areas Not Tested, Other supporting information:
Include in this section any assumptions, areas you will not be testing (but feel you should be) and any other information that will help explain your stategy, risks, etc.
Note on H34: Sylvia Ward: Please fill in with any additional comments.

## CRs
Area Path | Iteration Path | ID | Title | QA Writing Est | QA Testing Est | Focus Priority (1-4) | Comments | Link
PFEvatec\WF06 (Logbook)\Magnet Systems | Phase 2\R10\R10.2 | 286067 | Ticket #35008 - Tracking of magnet systems in Evatec Fabric | 8 | 23 | 1 | Impacts: - 32 requirements. QA Writing Approach: - Test case writing with assistance from Copilot for formatting to expedite. Happy path and unhappy path scenarios planned with edge cases and targeted regression cases for the multiple impacted areas. QA Testing Approach: - Verify Magnet System Type and Magnet System functionality, document management, permissions, inspection tracking, overdue calculations, and filter behavior. - Validate lifecycle workflows: checkout, return, install, uninstall, replace, retire, and label/QR generation. - Validate Standard to Prototype workflows including variant numbering, lineage, Article Number uniqueness, and promotion to Standard preserving associations. - Verify Hardware Configuration integration including the new Magnet System role type and serial number enforcement. - Validate Magnet System History and Logbook synchronization across all lifecycle events. - Verify Export Hardware Configuration includes Magnet System details. - Validate database migrations, entity relationships, and conversion of existing Hardware Components to Magnet Systems. - Perform regression testing on impacted areas. Potential Issues: - Highest-risk area of the release with broad cross-module impact across Hardware Configuration, Logbook, History, and Export. - Prototype lifecycle, Article Number uniqueness, and Standard/Prototype promotion may cause defects in lineage, history, or association preservation. - Migration of existing Hardware Components and Magnet System ↔ Logbook synchronization carry the highest regression and data-integrity risk. | Change Request 286067: Ticket #35008 - Tracking of magnet systems in Evatec Fabric
PFEvatec\WF06 (Logbook)\HW Config | Phase 2\R10\R10.2 | 285729 | Ticket #34951 - Search HW components | 1 | 3 | 2 | Impacts: - 3 requirements. QA Writing Approach: - Test case writing with assistance from Copilot for formating to expadite.Happy path and unhappy path scenarios planned with edge cases and regressions around modified requirements. QA Testing Approach: - Verify Search HW Components functionality across all impacted areas. - Execute positive, negative, partial-match, and no-result search scenarios. - Validate installed hardware components are returned correctly in search results. - Confirm consistent filtering, search results, and display behavior across all supported pages. Potential Issues: - Differences in page-level data loading, indexing, or caching could lead to inconsistent search behavior across the impacted areas. | Change Request 285729: Ticket #34951 - Search HW components
PFEvatec | Phase 2\R10\R10.2 | 286836 | Ticket #34948 - Article import | 2 | 3 | 3 | Impacts: - 2 requirements. QA Writing Approach: - Test cases will be created with Copilot assistance to expadite formatting and writing process, covering happy path, unhappy path, edge cases, and regression scenarios for impacted functionality. QA Testing Approach: - QA will verify custom import formats and mappings. - QA will validate hardware component imports using legacy and new file formats. - QA will confirm field mappings and numeric status values import correctly. - QA will verify partial imports do not incorrectly deactivate valid hardware components. - QA will perform regression testing on BOM Import, Work Order Import, and Hardware Component import workflows. Potential Issues: - Incorrect mappings may result in invalid imported data. - Import framework changes could affect existing import workflows. - Partial imports may incorrectly deactivate hardware components. - QA will validate import behavior and responsiveness for large import files. | Change Request 286836: Ticket #34948 - Article import
PFEvatec\WF02 (Box and Substrates)\Box Management | Phase 2\R10\R10.2 | 284111 | Ticket #34682 - WBS Element for self-service boxes | 0.5 | 3 | 4 | Impacts: - 2 requirements QA Writing Approach: - Test case writing with assistance from Copilot for formating to expadite. Happy path, unhappy path scenarios planned with some edge cases and regressions around modified requirements. QA Testing Approach: - Verify the WBS Element field across all impacted pages. - Create and edit self-service boxes with WBS Element values. - Confirm WBS Element values save correctly and persist after updates. - Validate consistent display of WBS Element values across all applicable pages. - Verify WBS Element values remain available and functional in related workflows. Potential Issues: - Differences in how each page loads or caches data could lead to inconsistent WBS Element behavior. | Change Request 284111: Ticket #34682 - WBS Element for self-service boxes
PFEvatec | Phase 2\R10\R10.2 | 290161 | Ticket #35623 - Error: Use PDT to create the tool definition for new tool type | 0 | 0 | N/A | Impacts: - 0 requirements. Note: - This item was logged as a CR because it introduces support for a new tool type rather than fixing an existing defect. - The change was delivered as a customer patch to unblock Hermann's tool setup activity. - Hermann validated the fix in his environment and closed the ticket. - No additional internal QA testing is planned. | Change Request 290161: Ticket #35623 - Error: Use PDT to create the tool definition for new tool type
|  |  | Ad Hoc Verification Time: | 0 | 3 |  | Allocate ad hoc verification time for exploratory testing and validation of impacted workflows not explicitly covered by formal test cases.
|  |  | Total Est Time: | 11.5 | 35

## Bugs
Bugs
Area Path | Iteration Path | ID | Title |  | QA Verification Est | Priority (1-4) | Comments | Link
PFEvatec | PFEvatec\Phase 2\R10\R10.1 | 285795 | Ticket #34217 - Article # with Project # in the Projects table |  | 0.5 | 2 | QA will do a quick sweep of related impacted UI areas to make sure nothing breaks from change related to bug. | Bug Ticket #34217 - Article # with Project # in the Projects table
|  |  |  | Additional Est Verification Time: | 9.5 |  | Rationale: Accounts for expected incoming bugs requiring verification. Estimate is based on the average bug verification effort observed during previous releases.
|  |  |  | Total Est Time: | 10

## Test Environments & VMs
Test Environments & VMs
Every project release requires testing on a specific environment (i.e., Windows 10 Enterprise LTSC 2019, 64-bit) or on multiple environments (i.e., development environment, regression testing, etc.). It is important to clarify in this section what environment(s) and what VM(s) you will be using / will need set up. If testing on multiple environments, list each test environment and VM separately.
Product version: | <Product name (i.e., PTO, EIB, PFSC) and version number>
License type to use: | 64bit, EDA, SECS/GEM, 300mm, E10, VA
Test environment: | <OS system/version>
VM available: | <Yes/No> | <VM Name>
Note on A7: Kristen Matsumoto: It is important to specify which license to use as there are many options. If not sure, ask your manager.
Note on A9: Tina Chonko: If testing in a development environment, indicate the version of Visual Studio and .NET used for testing.
Note on A10: Tina Chonko: Indicate VM to use or if one must still be set up. View the VM List on PEERHub for details about available VMs: https://vmlist.peergroup.com/

## Template Info & Doc Control
Template Information:
This template is intended for small/simple projects/product releases (e.g., service packs). Use the following guidelines: - QA effort is ~80 hours or less. If it is more, then you need permission from your project/product Manager to use the mini-STP. - Only 1 QA resource. If 2 QA resources (but other criteria apply), then add a Resource column to the right of the Timekeeping column. If >2 then use full STP. - There is no "manage" activity in the template because it is assumed it is small enough that it is not needed. It can be added if needed. - Do not use this STP template if testing SEMI standard changes (product) or kicking off test automation initiatives. - There is no "task" column because it is assumed that the Test task(s) will be linked to the Requirement/CR/Bug listed in each row. Basically, if you find that this template requires too much modification to outline your test strategy, then use the full STP.
Document Control Information:
Template Version: | 1.2
Release Date: | February 10, 2022
Document Owner: | Sylvia Ward
Approvers: | Services Management Team
Next Review Date: | February 10, 2024
Expiration Date: | May 10, 2024