## Overview
Evatec Factor - Release 10.0.0.6 - Mini Software Test Plan
Wrap-up: Actuals and analysis/comments
Rqmt/CR/Bug ID | Work Item Type |  | Timekeeping | Writing Estimate | Testing Estimate | Comments |  | Azure Writing Actuals | Azure Testing Actuals | Timekeeping Actuals | Comments
|  | Prepare Software Test Plan | Sys-Testing\plan |  | 2 |  |  |  |  | Get from TK
New Functionality
| Change Requests | Ad hoc testing | Sys-Testing\QA Test | 4 | 16 | Information found on Change Requests tab |  | Get From Azure | Get From Azure
|  | Total New - Writing | Sys-Testing\write | 4 |  |  |  | 0 |  | Get from TK | Comment if Azure & TK significantly different
|  | Total New - Testing | Sys-Testing\QA Test |  | 16 |  |  |  | 0 | Get from TK | Comment if Azure & TK significantly different
Regression
|  | Total Regression | Sys-Testing\regression | 0 | 4 | Describe your regression areas/strategy here. Add a tab if needed. ATP prep & execution go here. |  | Get from Azure | Get from Azure | Get from TK
General / Other
|  | Consult time with Dev | Sys-Testing \consult |  | 1 |  |  |  |  | Get from TK
|  | Environment Setup, installing builds | Sys-Testing \setup |  | 4 | Haven't set up environments in awhile, may introduce some complexity |  |  |  | Get from TK
|  | Bug verification | Sys-Testing\verify |  | 7 | Eight bugs to verify, expecting others as well |  |  |  | Get from TK
|  | Reviewing spec | Sys-Testing\review |  | 1 |  |  |  |  | Get from TK
|  | Unplanned changes / contingency | Sys-Testing\misc |  | 1 |  |  |  |  | Get from TK
|  | Total General |  |  | 14 |  |  |  |  | 0
|  |  | Grand Total (estimate) |  | 40 |  | Grand Total (actual) | 0 | 0 | 0
|  | Budget: | Hours:
|  | Budget (check TK or ask PM) | 40
|  | Estimated Effort | 40
|  | Difference (hours) | 0
|  | % Difference to Budget | 0%
|  | Actual Effort (hours) | 0
|  | Actual Effort (% Diff to Budget) | -100% |  |  | Assumptions, Areas Not Tested, Other supporting information:
Include in this section any assumptions, areas you will not be testing (but feel you should be) and any other information that will help explain your stategy, risks, etc.
Note on A1: Sylvia Ward: Update
Note on H31: Sylvia Ward: Please fill in with any additional comments.

## Change Requests
Change Requests
Area Path | Iteration Path | ID | Title | Developer Estimate |  | QA Writing Est | QA Testing Est | Comments | Link
PFEvatec\WF01 (Tool Configuration)\Modules | PFEvatec\Phase 2\R10\R10.0\R10.0.6 | 211377 | Ticket #20867 - Create / Manage Modules for File Tools | 12 |  | 1 | 4
PFEvatec\WF04 (Substrate Browsing and Analysis)\History | PFEvatec\Phase 2\R10\R10.0\R10.0.6 | 214983 | Ticket #19857 - Manual tool - edit data | 12 |  | 1 | 5
PFEvatec\WF01 (Tool Configuration)\Tools\SECS-GEM | PFEvatec\Phase 2\R10\R10.0\R10.0.6 | 233611 | Ticket #24299 - Module positions only once in Tool View | 1 |  | 0.25 | 0.5
PFEvatec\WF08 (DB) | PFEvatec\Phase 2\R10\R10.0\R10.0.6 | 261053 | Ticket #29110 - Manual data input of Work Orders | 4 |  | 0.5 | 1.5
PFEvatec | PFEvatec\Phase 2\R10\R10.0\R10.0.6 | 261151 | Ticket #28140 - Display of chuck number for BPME tools | 8 |  | 1.25 | 3
[5 empty] | Total Est Time: | 4 | 14

## Test Environments & VMs
Test Environments & VMs
Every project release requires testing on a specific environment (i.e., Windows 10 Enterprise LTSC 2019, 64-bit) or on multiple environments (i.e., development environment, regression testing, etc.). It is important to clarify in this section what environment(s) and what VM(s) you will be using / will need set up. If testing on multiple environments, list each test environment and VM separately.
Product version: | <Product name (i.e., PTO, EIB, PFSC) and version number>
License type to use: | 64bit, EDA, SECS/GEM, 300mm, E10, VA
Test environment: | <OS system/version>
VM available: | <Yes/No> | <VM Name>
Note on A7: Kristen Matsumoto: It is important to specify which license to use as there are many options. If not sure, ask your manager.
Note on A9: Tina Chonko: If testing in a development environment, indicate the version of Visual Studio and .NET used for testing.
Note on A10: Tina Chonko: Indicate VM to use or if one must still be set up. View the VM List on PEERHub for details about available VMs: https://vmlist.peergroup.com/

## Template Info & Doc Control
Template Information:
This template is intended for small/simple projects/product releases (e.g., service packs). Use the following guidelines: - QA effort is ~80 hours or less. If it is more, then you need permission from your project/product Manager to use the mini-STP. - Only 1 QA resource. If 2 QA resources (but other criteria apply), then add a Resource column to the right of the Timekeeping column. If >2 then use full STP. - There is no "manage" activity in the template because it is assumed it is small enough that it is not needed. It can be added if needed. - Do not use this STP template if testing SEMI standard changes (product) or kicking off test automation initiatives. - There is no "task" column because it is assumed that the Test task(s) will be linked to the Requirement/CR/Bug listed in each row. Basically, if you find that this template requires too much modification to outline your test strategy, then use the full STP.
Document Control Information:
Template Version: | 1.2
Release Date: | February 10, 2022
Document Owner: | Sylvia Ward
Approvers: | Services Management Team
Next Review Date: | February 10, 2024
Expiration Date: | May 10, 2024