## Overview
3401INT GLP TA/TC PTO 9 - Summit - Release - WW05 GLP - Mini Software Test Plan
Wrap-up: Actuals and analysis/comments
Rqmt/CR/Bug ID | Work Item Type |  | Timekeeping | Writing Estimate | Testing Estimate | Comments |  | Azure Writing Actuals | Azure Testing Actuals | Timekeeping Actuals | Comments
|  | Prepare Software Test Plan | 3401INT GLP TA PTO 9\Sys-Testing\plan | 3 |  | Time est. includes draft, review, and edits after suggestions |  |  |  | Get from TK
New Functionality
| TA Requirements | See 'Requirements' tab for detailed breakdown | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\<QA Test - Write> | 10 | 27 | TA requirements for GLP are the bulk of writing and testing |  | Get From Azure | Get From Azure
| TC Requirements | See 'Requirements tab for detailed breakdown | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\<QA Test - Write> | 2 | 10 | TC requirements for GLP are all focused on SkyRunner suite |  | Get From Azure | Get From Azure
| n/a | Ad hoc testing | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\QA Test |  | 7 | This includes estimated time for abnormal testing |  | Get From Azure | Get From Azure
|  | Total New - Writing | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\QA Write | 12 |  | Writing includes abnormal and non-happy path tests |  | 0 |  | Get from TK | Comment if Azure & TK significantly different
|  | Total New - Testing | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\QA Test |  | 44 | Testing includes abnormal and non-happy paths |  |  | 0 | Get from TK | Comment if Azure & TK significantly different
Regression
|  | Total Regression | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Regression | 0 | 5 | Targeted manual regression on impacted areas and SkyRunner automated tests |  | Get from Azure | Get from Azure | Get from TK
General / Other
| n/a | Consult time with Dev | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Consult |  | 0.5 | Note: I did not create tasks for this item, will just be added to time keeping |  |  |  | Get from TK
| n/a | Environment Setup, installing builds | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Setup |  | 2 | Note: I did not create tasks for this item, will just be added to time keeping |  |  |  | Get from TK
| n/a | Bug verification | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Verify |  | 6 | Note: I did not create tasks for this item, will just be added to time keeping |  |  |  | Get from TK
| n/a | Test case reviews | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Review |  | 1 | Note: I did not create tasks for this item, will just be added to time keeping |  |  |  | Get from TK
| n/a | Release | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Release |  | 4 | Note: I did not create tasks for this item, will just be added to time keeping |  |  |  | Get from TK
| n/a | Unplanned changes / contingency | 3401INT GLP <TA-TC> PTO 9\Sys-Testing\Misc |  | 0.5 | Note: I did not create tasks for this item, will just be added to time keeping |  |  |  | Get from TK
|  | Total General |  |  | 14 |  |  |  |  | 0
|  |  | Grand Total (estimate) |  | 75 |  | Grand Total (actual) | 0 | 0 | 0
|  | Budget: | Hours:
|  | Budget (check TK or ask PM) | 60
|  | Estimated Effort | 75
|  | Difference (hours) | 15
|  | % Difference to Budget | 25%
|  | Actual Effort (hours) | 0
|  | Actual Effort (% Diff to Budget) | -100% |  |  | Assumptions, Areas Not Tested, Other supporting information:
Include in this section any assumptions, areas you will not be testing (but feel you should be) and any other information that will help explain your stategy, risks, etc.
Note on H35: Sylvia Ward: Please fill in with any additional comments.

## Requirements
Requirements
Area Path | Iteration Path | ID | Requirement | Developer Estimate |  | QA Writing Est | QA Testing Est | Comments | Link
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252929 | PickAndPlaceBuffer Refactor (Tool Model) | 24 |  | 0.5 | 2.5 | Mostly tested by Hardware during integration, we don't need to go through hardware. Base testing can be performed. | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252929
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252933 | Tray Scheduler (Tool Model) | 8 |  | 1 | 2 | Need to confirm that no tray dispatching occurs | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252933
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252930 | Chiller Component (Tool Model) | 4 |  | 0.5 | 0 | No changes made -Should be tested during regression. | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252930
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252931 | LTIM Component (Tool Model) | 4 |  | 0.5 | 0 | No changes made -Should be tested during regression. | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252931
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252932 | Unit Scheduler (Tool Model) | 32 |  | 2 | 3 | Extensive changes for this task, may require more time than estimate, majority of work appears to be on developer side | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252932
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252934 | Simulation (Internal Services) | 4 |  | 1 | 4 | Extensive changes for this task, may require more time than estimate, majority of work appears to be on developer side | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252934
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252935 | SkyRunner Support (Simulation) | 12 |  | 0.5 | 1 | May overlap with SkyRunner TC testing | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252935
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252936 | Recipe Service (Internal Services) | 8 |  | 0.5 | 1.5 | Should be able to utilize chiller recipe --> via hdmx. Test multiple hdmx recipes with hdmx | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252936
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252937 | Component Monitoring Service (Internal Services) | 6 |  | 0 | 0 | Confirm not required to test. Will be tested during integration. | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252937
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252938 | TC Lite Cycling (Internal Services) | 6 |  | 2.5 | 10 | Changes to TC Lite Cycling could cause issues (issue prone area based on other testing). Confirm changes to existing funcitonality, can compare with earlier builds for reference. This should be bulk of testing. | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252938
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252939 | RAL Cycling (TC Lite Cycling) | 20 |  | 1 | 3 | Important requirement - should be tested at same time as other TC Lite Cycling as well | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252939
PTOAEM\Summit\GLP | PTOAEM\Horizon\Skyline 4.0\2025\WW06 GLP | 252940 | GLP Backwards Compatibility (External Interfaces) | 40 |  | 0 | 0 | Testing for this can only be done by dev unit tests or during integration. Testing time should instead be utilized for regression | https://ops1.peergroup.com/DefaultCollection/PTOAEM/_workitems/edit/252940
[5 empty] | Total Est Time: | 10 | 27 | Add these values to main Overview tab
PTOIntelTester\Summit\GLP | PTOIntelTester\Horizon\Skyline 4.0\2025\WW06 GLP | 259685 | SkyRunner RAL Loading (SkyRunner) | 8 |  | 1 | 3 | Confirming functionality in logs after running tests in Kubernetes, could run tests locally as well to confirm - regression --- > multiprocess step --> binning.... | https://ops1.peergroup.com/DefaultCollection/PTOIntelTester/_workitems/edit/259685
PTOIntelTester\Summit\GLP | PTOIntelTester\Horizon\Skyline 4.0\2025\WW06 GLP | 259686 | SkyRunner TestPlan Definition (SkyRunner) | 16 |  | 1 | 7 | Ensure SkyRunner test plan created by developer targets required areas and tests are functional. Brendan is writing so time for QA would mostly be updating test suite / executing tests / logging results / failed. | https://ops1.peergroup.com/DefaultCollection/PTOIntelTester/_workitems/edit/259686
[5 empty] | Total Est Time: | 2 | 10 | Add these values to main Overview tab
Digital UNIT --> covered --- > .. ad hoc / tc lite cycling
Manual trays in ad hoc regression -->

## Test Environments & VMs
Test Environments & VMs
Every project release requires testing on a specific environment (i.e., Windows 10 Enterprise LTSC 2019, 64-bit) or on multiple environments (i.e., development environment, regression testing, etc.). It is important to clarify in this section what environment(s) and what VM(s) you will be using / will need set up. If testing on multiple environments, list each test environment and VM separately.
Product version: | 3401INT GLP TA/TC PTO 9
License type to use: | PTO 9
Test environment: | Linux Container
VM available: | Yes - but not required. | hbi1064ql14-qa1

## Template Info & Doc Control
Template Information:
This template is intended for small/simple projects/product releases (e.g., service packs). Use the following guidelines: - QA effort is ~80 hours or less. If it is more, then you need permission from your project/product Manager to use the mini-STP. - Only 1 QA resource. If 2 QA resources (but other criteria apply), then add a Resource column to the right of the Timekeeping column. If >2 then use full STP. - There is no "manage" activity in the template because it is assumed it is small enough that it is not needed. It can be added if needed. - Do not use this STP template if testing SEMI standard changes (product) or kicking off test automation initiatives. - There is no "task" column because it is assumed that the Test task(s) will be linked to the Requirement/CR/Bug listed in each row. Basically, if you find that this template requires too much modification to outline your test strategy, then use the full STP.
Document Control Information:
Template Version: | 1.2
Release Date: | February 10, 2022
Document Owner: | Sylvia Ward
Approvers: | Services Management Team
Next Review Date: | February 10, 2024
Expiration Date: | May 10, 2024