## Overview
Evatec Factor - Release 10.0.0.8 - Mini Software Test Plan
Wrap-up: Actuals and analysis/comments
Rqmt/CR/Bug ID | Work Item Type |  | Timekeeping | Writing Estimate | Testing Estimate | Comments |  | Azure Writing Actuals | Azure Testing Actuals | Timekeeping Actuals | Comments
|  | Prepare Software Test Plan | Sys-Testing\plan |  | 1 |  |  |  |  | Get from TK
New Functionality
| Change Requests | Ad hoc testing | Sys-Testing\QA Test | 1 | 2 | Information found on Change Requests tab |  | Get From Azure | Get From Azure
|  | Total New - Writing | Sys-Testing\write | 3 |  |  |  | 0 |  | Get from TK | Comment if Azure & TK significantly different
|  | Total New - Testing | Sys-Testing\QA Test |  | 17 |  |  |  | 0 | Get from TK | Comment if Azure & TK significantly different
Regression
|  | Total Regression | Sys-Testing\regression | 0 | 0.5 | Perform quick manual smoke test around changes |  | Get from Azure | Get from Azure | Get from TK
General / Other
|  | Consult time with Dev | Sys-Testing \consult |  | 0.5 |  |  |  |  | Get from TK
|  | Environment Setup, installing builds | Sys-Testing \setup |  | 3 | Haven't set up environments in awhile, which can introduce some complexity |  |  |  | Get from TK
|  | Bug verification | Sys-Testing\verify |  | 5 | Four external bugs to verify, adding some time for internal issues as well |  |  |  | Get from TK
|  | Unplanned changes / contingency | Sys-Testing\misc |  | 1 |  |  |  |  | Get from TK
|  | Total General |  |  | 9.5 |  |  |  |  | 0
|  |  | Grand Total (estimate) |  | 31 |  | Grand Total (actual) | 0 | 0 | 0
|  | Budget: | Hours:
|  | Budget (check TK or ask PM) | 40
|  | Estimated Effort | 31
|  | Difference (hours) | -9
|  | % Difference to Budget | -22.5%
|  | Actual Effort (hours) | 0
|  | Actual Effort (% Diff to Budget) | -100% |  |  | Assumptions, Areas Not Tested, Other supporting information:
Include in this section any assumptions, areas you will not be testing (but feel you should be) and any other information that will help explain your stategy, risks, etc.
Note on A1: Sylvia Ward: Update
Note on H30: Sylvia Ward: Please fill in with any additional comments.

## Change Requests
Change Requests
Area Path | Iteration Path | ID | Title | Developer Estimate |  | QA Writing Est | QA Testing Est | Comments | Link
PFEvatec\WF00 (Core) | PFEvatec\Phase 2\R10\R10.0\R10.0.8 | 228689 | Ticket #23360 - Sorting predefiend type values |  |  | 0.25 | 0.5
PFEvatec\WF06 (Logbook)\HW Config | PFEvatec\Phase 2\R10\R10.0\R10.0.8 | 231083 | Ticket #23423 - collapse all in hardware list |  |  | 0.25 | 0.25
PFEvatec\WF02 (Box and Substrates) | PFEvatec\Phase 2\R10\R10.0\R10.0.8 | 233500 | Ticket #24059 - Automatic ECL Box Reminder |  |  | 0.25 | 0.75
PFEvatec\WF08 (DB)\BPS | PFEvatec\Phase 2\R10\R10.0\R10.0.8 | 269207 | Ticket #32097 - Project (Work Order) upload from Excel |  |  | 0.25 | 0.5
PFEvatec\WF04 (Substrate Browsing and Analysis)\Substrates | PFEvatec\Phase 2\R10\R10.0\R10.0.8 | 225471 | Ticket #22904 - Modify Tracking data |  |  | 1 | 8
PFEvatec\WF03 (Process and Measure) | PFEvatec\Phase 2\R10\R10.0\R10.0.8 | 235679 | Ticket #29725 - Store files/manual data against modules |  |  | 1 | 7
[5 empty] | Total Est Time: | 3 | 17

## Template Info & Doc Control
Template Information:
This template is intended for small/simple projects/product releases (e.g., service packs). Use the following guidelines: - QA effort is ~80 hours or less. If it is more, then you need permission from your project/product Manager to use the mini-STP. - Only 1 QA resource. If 2 QA resources (but other criteria apply), then add a Resource column to the right of the Timekeeping column. If >2 then use full STP. - There is no "manage" activity in the template because it is assumed it is small enough that it is not needed. It can be added if needed. - Do not use this STP template if testing SEMI standard changes (product) or kicking off test automation initiatives. - There is no "task" column because it is assumed that the Test task(s) will be linked to the Requirement/CR/Bug listed in each row. Basically, if you find that this template requires too much modification to outline your test strategy, then use the full STP.
Document Control Information:
Template Version: | 1.2
Release Date: | February 10, 2022
Document Owner: | Sylvia Ward
Approvers: | Services Management Team
Next Review Date: | February 10, 2024
Expiration Date: | May 10, 2024